Project Charter

Enterprise Retail & Strategic Inventory System

# Version Control

| Version | Date | Summary of changes |
| --- | --- | --- |
| 1 | 24/02/2026 | Initial version of the Project Charter |

# Project Justification

The Enterprise Retail & Strategic Inventory System is designed for a large retail shop in Nepal, which still relies on handwritten billing and lack proper inventory management system. This manual process results in billing errors, poor product record management, difficulty in tracking sales and stock levels, and consumes customer time. Additionally, customers are unable to track their purchase history, which directly affects customer experience. Although big franchises such as "Big Mart" and "Bhat-Bhateni" have their own advanced billing and product management systems, these systems are expensive and not affordable for many large independent retail shops in Nepal. Thus, our goal is to create a lightweight, cost-effective, and efficient version of the same system that helps the user track their sales and product data. The proposed system will automate billing through barcode scanning system and inventory tracking while maintaining accurate sales and product records. The software will be used by the shop owner, cashiers, and customers of the retail shop. By reducing manual billing errors, saving time, improving sales tracking, and enhancing stock management, the system is expected to increase profit and improve overall customer satisfaction. Therefore, this system aims to transform traditional retail operations into a more efficient, accurate, and digitally managed business environment.

# Project Scope

In Scope: - System Development - Development of a web-based billing and inventory System to manage products, sales records and billing operations. - A mobile application (React Native) that allows customers to track their purchase history. - A backend system using FastAPI to handle business logic and system operations. - MySQL database for storing users, products, transactions, and inventory records. - IoT Billing Integration - An IoT-based system barcode scanning system using ESP32 and a barcode scanning module with the MQTT protocol. - Core Functional Features - Implementation of security features, including JWT-based authentication, bcrypt password hashing and email OTP-based two-factor authentication (2FA). - Real-time dashboard updates using WebSocket technology. - AI & Analytics - Basic sales forecasting using historical transaction data. - RAG-based chatbot for answering queries related to user’s data. - Deployment & Testing - Docker containerization and deployment using Docker Compose. - Functional and performance testing of the system. Out of Scope: - Large-scale enterprise deployment. - Commercial cloud hosting and high-availability clustering. - Multi-branch retail chain integration. - Advanced financial accounting systems. - Integration with external payment gateways. - Production-level cybersecurity auditing. - Large-scale distributed microservice orchestration.

High-Level Requirements Functional Requirements - The system shall provide separate dashboards for Admin, Cashier and Customer. - The system shall support customer registration and login system - The system shall enable billing operations for product purchases. - The system shall track and record sales transactions. - The system shall manage product records, including adding, updating, and deleting products. - The system shall support barcode-based billing using a barcode scanner. - The system shall provide AI- based features such as sales forecasting and a chatbot. Non-Functional Requirements - The system shall ensure password security using encryption (bcrypt hashing). - The system shall implement secure authentication using JWT. - The system shall provide real-time data updates. - The system shall maintain performance efficiency during peak usage. - The system shall ensure data reliability and availability.

# Duration

| Phase | Week | Focus |
| --- | --- | --- |
| Planning & Requirements | 1 | Requirement specification and Architecture design |
| Database Design and design | 2-3 | ERD, API design, UI wireframes |
| Core Backend Development | 4-6 | Billing, inventory, authentication APIs |
| Frontend Development | 5-7 | Web dashboard implementation |
| IoT Integration | 8 | ESP32 + MQTT integration |
| AI Module Implementation | 9 | Sales forecasting prototype |
| System Integration | 10 | Full-stack integration |
| Testing & Optimization | 11 | Functional & performance testing |
| Deployment & Documentation | 12 | Docker deployment & final documentation |

# Estimated Budget

Hardware Cost (Prototype) - ESP32 Microcontroller – Approx. NPR 2,000 - Barcode Scanning module – Approx. NPR 3,500 - Other Electronic Components – Approx. NPR 500 Estimated Total Hardware Cost: NPR 6,000 – NPR 7,000 Software Cost - All software tools and technologies used in this project are open source. Deployment will use local or academic infrastructure. Therefore, no additional software cost is required. Estimated Effort - Estimated effort per person per week: 12 – 14 hours - Estimated total group effort per week: 72 – 84 hours - Estimated total effort for 12 weeks: 864 – 1008 hours

# Roles and Responsibilities

| Name | Role |
| --- | --- |
| Simona Kattel (24030159) |  |
| Sachin Maharjan (24036543) |  |
| Pradip Yadav (24036544) |  |
| Aayushma Dhakal (24030146) |  |
| Abhinav Sitaula (23085179) |  |
| Bardan Thapa (23085198) |  |