Project Risk Register

Project: Enterprise Retail & Strategic Inventory System

Risk Register Table

| ID | Risk | Risk Description | L | I | Sev | Owner | Mitigation Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Team Member Unavailability | A group member may become unavailable due to illness or other personal issues, causing delays to assigned modules and placing undue burden on remaining members. | 3 | 3 | 9 | Project Manager | Maintain a shared task tracker like GitHub or Trello. Ensure all code is reviewed and documented so any member can pick up another’s work. | Open |
| R2 | Stakeholder Disagreement | Differences in expectations between group members or simulated stakeholders regarding system features, design, or scope may result in rework and late deliveries. | 2 | 3 | 6 | Project Manager | Conduct regular reviews meeting with the project supervisor. Maintain clear documentation of agreed requirements in a shared repository. Use Figma prototypes to validate UI decisions early before development. | Open |
| R3 | IoT Hardware Failure | The ESP32 microcontroller or barcode scanner module may malfunction, fail to initialize or become damaged during development and live use, stopping the billing process completely. | 3 | 4 | 12 | IoT Lead | Purchase at least two backup ESP32 units and scanner modules. Implement a software backup that allows manual backup entry through the web interface if the IoT system is unavailable. | Open |
| R4 | AI Forecast Inaccuracy | The scikit-learn forecasting model may produce unreliable predictions if trained on insufficient data, failing to meet the target error rate below 15% | 3 | 3 | 9 | AI/ML Lead | Create or look for a valid transaction dataset from Kaggle that reflects seasonal trends. Test multiple regression models. Monitor performance using RMSE and MAE and retrain the model if performance thresholds are exceeded. | Open |
| R5 | Database Data Loss | Accidental deletion, schema migration errors, or container volume misconfiguration in Docker could result in permanent loss of transaction records, inventory data and audit logs. | 2 | 5 | 10 | Backend Lead | Set up automated daily MySQL backups using Docker volume mounts to a persistent host path. Tests restore procedures monthly and implement transaction rollback mechanisms in FastAPI. | Open |
| R6 | RAG Chatbot Irrelevant Responses | The RAG-based chatbot may generate inaccurate or hallucinated responses if the vector store is poorly populated, embeddings are mismatched or the LLM API returns incorrect context. | 3 | 3 | 9 | AI/ML Lead | Build a comprehensive knowledge base of store-related FAQs. Apply semantic similarity thresholds to filter out low-confidence results and provide a default response when necessary. Conduct user testing to validate effectiveness. | Open |
| R7 | Poor Version Control Practices | Merge conflicts, accidental commits to the main branch, or a lack of a structured branching strategy may corrupt the codebase, particularly when several developers are working on interconnected modules simultaneously. | 3 | 3 | 9 | Project Manager | Implement a Git branching strategy like Git Flow. Protect the main branch with mandatory pull request reviews. Conduct weekly merge sessions to resolve conflicts before they build up. | Open |
| R8 | Copyright and licensing issues | The use of third-party libraries, open-source models, or LLM APIs with restrictive licenses may unintentionally violate their terms, especially in commercial applications or public demonstration purpose. | 2 | 3 | 6 | Project Manager | Audit all dependencies for license compatibility using tools like “pip-licenses” and “license-checker”. Prefer libraries with MIT or Apache 2.0 licenses. Document all third-party components in the project report. | Open |
| R9 | Cybersecurity Attack (SQL Injection / XSS) | The FastAPI backend may be vulnerable to SQL Injection, XSS, or API abuse if validation is weak. | 3 | 5 | 15 | Backend Lead | Use parameterized queries (ORM), input validation (Pydantic), rate limiting, JWT expiry, HTTPS. Immediate patch, revoking tokens, restoring clean DB backup | Open |
| R10 | MQTT Communication Failure | MQTT broker downtime may stop barcode scan transmission from ESP32. | 3 | 4 | 12 | IoT Lead | Use persistent sessions, QoS level 1, broker monitoring. Manual billing fallback via web interface. | Open |
| R11 | WebSocket Real-Time Sync Failure | WebSocket disconnection may prevent real-time dashboard updates. | 3 | 3 | 9 | Backend Lead | Auto-reconnecting logic, fallback polling API. We can use Temporary refresh-based dashboard updates. | Open |
| R12 | Email OTP Delivery Failure | Email OTP may fail due to SMTP restrictions or spam filtering. | 2 | 4 | 8 | Backend Lead | Use reliable SMTP, retry mechanism. Temporary admin manual activation. | Open |
| R13 | Docker Misconfiguration | Incorrect Docker Compose setup may break environment consistency. | 3 | 3 | 9 | Backend Lead | Using environment variables and test staging container builds. We can also roll back to last stable image. | Open |
| R14 | Data Privacy Compliance Issue | Mishandling customer transaction data may violate data protection laws in Nepal. | 2 | 5 | 10 | Project Manager | Encrypting sensitive fields, role-based access control. | Open |
| R15 | Incomplete Testing Coverage | Lack of proper unit/integration testing may allow hidden bugs. | 3 | 4 | 12 | QA Lead | Using Jest for frontend and Pytest for backend, code coverage tracking. Allocating final sprint exclusively for bug fixing. | Open |

Notes

L = Likelihood

I = Impact

Sev = Severity (L * I)

All ratings use a scale of 1 (Very Low) to 5 (Very High).

This register must be reviewed at each project sprint review and updated whenever new risks arise or existing risks materialize.